|  |  |
| --- | --- |
|  | IDC-4942- Capstone  Fall 2021 |

**Weekly Log**

***2021-10-23***

|  |  |
| --- | --- |
| **Group Project Name:** | **The Three Musketeers** |
| **Sponsor Company:** | **Tallahassee Memorial Healthcare** |
| **Group Members:** | **Hailey Skoglund, Gus Lipkin, Maverick Hope** |

**Summary of Weekly Progress:**

* Centeno has received a data use agreement and has passed it on to Poly’s legal office and we are waiting for approval.
* Did presentation in class.

**Summary of what was planned for this week but wasn’t completed and why (if applicable):**

* We wanted to do an exploratory analysis of the data to get acquainted with it and determine next steps. We haven’t received the data from TMH yet.

**Summary of what is planned for this week:**

* Get access to the data so that we can do our exploratory analysis.
* Review copies of both health surveys
* Create WBS and project charter
* Write the midterm report

**Task accomplished by each member:**

* **Hailey:** 
  + Wrote and presented PowerPoint in class
  + Emailed sponsor about project generated IP and whether the students or TMH own it
  + Read sponsor’s replies to questions from the October 13 meeting
* **Gus:** 
  + Wrote and presented PowerPoint in class
  + Read sponsor’s replies to questions from the October 13 meeting
* **Maverick:**
  + Staying in contact with Dr. Centeno through after class chats
  + Presented slideshow in class
  + Read sponsor’s replies to questions from the October 13 meeting

**Blocking issues:**

* Legal must review DUA
* Data must be packaged by TMH who are still waiting to get the data from their third party data collection service

**Questions or Ideas:**

* Have the other groups been able to get access to their data?