|  |  |
| --- | --- |
|  | IDC-4942- Capstone  Fall 2021 |

**Weekly Log**

***2021-11-13***

|  |  |
| --- | --- |
| **Group Project Name:** | **The Three Musketeers** |
| **Sponsor Company:** | **Tallahassee Memorial Healthcare** |
| **Group Members:** | **Hailey Skoglund, Gus Lipkin, Maverick Hope** |

**Summary of Weekly Progress:**

* Received the data from Jessica and reviewed it
* Cleaned data and found outliers such as people who had their age above 150 years old
* Met with Jessica to go over the data and to receive the data dictionary
* Began the exploratory data analysis

**Summary of what was planned for this week but wasn’t completed and why (if applicable):**

* We were able to accomplish everything that we had planned for this week

**Summary of what is planned for this week:**

* Continue the exploratory data analysis
* Stay in contact with Jessica about any issues that we run into
* Find out what TMH wants to do for the IP form

**Task accomplished by each member:**

* **Hailey:** 
  + Emailed Jessica Parker for updates on getting the data
  + Set up meeting with Jessica to go over the data
  + Reviewed the data before meeting and prepared questions
  + Emailed meeting minutes to Jessica
  + Met with Jessica
  + Worked on EDA
  + Went to The Joinery for team bonding
* **Gus:** 
  + Reviewed the data before the meeting with Jessica and prepared questions
  + Cleaned the data
  + Met with Jessica
  + Wrote meeting minutes
  + Worked on EDA
  + Went to The Joinery for team bonding
* **Maverick:**
  + Reviewed the data before the meeting with Jessica and prepared questions
  + Met with Jessica
  + Worked on EDA
  + Went to The Joinery for team bonding

**Blocking issues:**

* None 😊

**Questions or Ideas:**