|  |  |
| --- | --- |
|  | IDC-4942- Capstone  Spring 2022 |

**Weekly Log**

***Week Number 7***

|  |  |
| --- | --- |
| **Group Project Name:** | **The Three Musketeers** |
| **Sponsor Company:** | **Tallahassee Memorial Healthcare** |
| **Group Members:** | **Hailey Skoglund, Gus Lipkin, Maverick Hope** |

**Summary of Weekly Progress:**

* **Continued interpreting and analyzing results**
* **Start writing up analysis for paper**
* **Got feedback from Jessica regarding HCAHPs numbering discrepancy and made appropriate adjustments.**

**Summary of what was planned for this week but wasn’t completed and why (if applicable):**

* **None**

**Summary of what is planned for this week:**

* **Start creating PowerPoint Presentation**

**Task accomplished by each member:**

* **Hailey:**
  + **Emailed Jessica to share progress and updates**
  + **Started writing paper**
  + **Wrote the weekly progress update**
* **Gus:**
  + **Uploaded progress to Github**
  + **Started writing paper**
  + **Made adjustments to account for HCAHPs numbering data**
* **Maverick:**
  + **Stayed in the loop with progress and sponsor communication**
  + **Started writing paper**

**Blocking issues:**

* **None**

**Questions or Ideas:**

* **None**